## Sheet2
Values
MPS ID | Stage | Current TAT (S50 onward) | Count of S200 TAT | Count of S300A TAT | Count of S300 TAT | Count of S600 TAT | Count of S650 TAT
Bibri, Simon Elias | S300 | 32 | 1 | 1 | 1
Metsoc Vol-I-8771046 | S300 | 32 | 1 | 1 | 1 | 1
Metsoc Vol-II-8771047 | S300 | 32 | 1 | 1 | 1
Metsoc Vol-IV-8771049 | S300 | 35 | 1 | 1 | 1
Metsoc Vol-V-8771050 | S300 | 40 | 1 | 1 | 1
Metsoc Vol-VII-8771052 | S300 | 40 | 1 | 1 | 1 | 1
Metsoc Vol-VIII-8771060 | S300 | 34 | 1 | 1 | 1
Grand Total |  |  | 7 | 7 | 7 | 2

## Current Status
S. no | Book ID | MPS ID | Stage | Received Date (S50) | Current TAT (S50 onward) | S200 TAT | S300A TAT | S300 TAT | S600 TAT | S650A TAT | S650 TAT | Total Chapters | MS Pages | Status - S200 | Status - 300 | Remarks | Column1 | Plateform | Column2
1 | 705744_1_En | Sánchez, Angeles | S600 | 2026-08-24 | 65 | 26 | 33 | 2 | 3 |  |  | 32 | 500 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 28 Chaps-Rev.delivered, 3 Part in Eproof, FM-recept error | GraySci-Template issue resolved on 6-Oct.Pls follow Instruction of Janet provided on 22-Oct. Chap-09- "There are some things that need to be revised: 1. The keywords for the Pasuruan regency should be Pasuruan Regency. Big R for Regency. 2. Images on Figures 6 and 7 were reversed; the image on Figure 7 should come first. 3. The captions on Figure 3.1 should be placed before Figure 1. 4. The captions on Figure 4.1 should be placed before Figure 13. | FM1 receipt error | Word
2 | 696264_1_En | Metsoc Vol-I-8771046 | S300 | 2026-09-26 | 32 | 14 | 14 | 2 | 0 |  |  | 15 | 200 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Delivered on 27th | email sent to PE (MS ISSUE) | Delayed from VE | Word
3 | 696260_1_En | Metsoc Vol-II-8771047 | S600 | 2026-09-26 | 32 | 16 | 10 | 5 | 0 |  |  | 15 | 200 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | email sent to PE (MS ISSUE) |  | Word
4 | 695444_1_En | Metsoc Vol-III-8771048 | S600 | 2026-09-23 | 35 | 15 | 16 | 1 | 1 |  |  | 31 | 280 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 completed | PRR Sent on 15th Sep | FM1 receipt error | Word
5 | 695897_1_En | Metsoc Vol-IV-8771049 | S300 | 2026-09-23 | 35 | 12 | 13 | 0 |  |  |  | 25 | 240 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 5 chap in Revises | PRR Sent on 15th Sep, Job Sheet updated for missing chapters and TOC on 10-Oct | Final Manuscript recd on 20th Oct | Word
6 | 696258_1_En | Metsoc Vol-V-8771050 | S300 | 2026-09-18 | 40 | 16 | 16 | 3 |  |  |  | 25 | 244 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Delivered S300 on 28-Oct | PRR Sent on 15th Sep, | Chap-04 removed as per author instructions | Word
7 | 696262_1_En | Metsoc Vol-VI-8771051 | S650A | 2026-09-18 | 40 | 16 | 7 | 8 | 4 | 1 |  | 9 | 100 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | PRR Sent on 15th Sep |  | Word
8 | 695893_1_En | Metsoc Vol-VII-8771052 | S600 | 2026-09-18 | 40 | 18 | 12 | 3 | 0 |  |  | 13 | 120 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Delivrered | PRR Sent on 15th Sep |  | Word
9 | 696253_1_En | Metsoc Vol-VIII-8771060 | S300 | 2026-09-24 | 34 | 33 | 12 | 3 |  |  |  | 37 | 200 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | All in revises | Received in Production on 18th Sep (2.50pm) | Delayed from VE | Word
10 | 696263_1_En | Metsoc-Vol-IX-8771159 | S300A | 2026-09-30 | 28 | 15 | 0 |  |  |  |  | 78 | 750 | S200 - Login :00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 11 chaps in Revises | Query solved on 12-Oct(FM component recd. Autho & Aff missing in chap-60) |  | Word
11 | 708036_1_En | Zhou, Kun-8770838 | S300A | 2026-09-28 | 30 | 21 | 2 |  |  |  |  | 81 | 600 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 25 chap in Revises | PRR sent on 17th Sep |  | Word
12 | 702839_1_En | Abarzhi, Snezhana I. | S650 | 2026-09-21 | 37 | 16 | 21 | 5 | 1 | 1 | 0 | 7 | 100 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 2 in Eproof rest revises completed | PRR sent on 17th Sep. Query-Reference missing and content mismatch, One new manuscript approval |  | Word
13 | 704353_1_En | Giordano, Andrea | S650A | 2026-09-17 | 41 | 19 | 13 | 1 | 1 | 2 |  | 41 | 500 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | PRR sent on 17th Sep |  | Word
14 | 708652_1_En | García-Holgado, Alicia-8771063 | S200 | 2026-09-29 | 29 | 25 | [5 empty] | 36 | 500 | S200 - Login : 00 Chapters; PE : 15 Chapters; CE : 21 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Query will be resolved after 23-oct conferences | Hold for new manuscript solved. Will receive today |  | Tex
15 | 709492_1_En | Trapani, Ferdinando | S300A | 2026-09-27 | 31 | 29 | 0 | 0 |  |  |  | 31 | 500 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S200 delivered on 27-Oct |  |  | Word
16 | 704172_1_En | Bibri, Simon Elias | S300 | 2026-09-26 | 32 | 24 | 5 | 0 |  |  |  | 28 | 350 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | 15 Chaps in Revises. |  |  | Word
17 | 710752_1_En | Xu-MSEM-8771092-Tex | S200 | 2026-10-07 | 21 | 7 | [5 empty] | 135 | 1500 | S200 - Login : 129 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Query for JS regarding mismatch in chaps. BM is also there+Index | Books should be spilit in Two vol-I and II in S600 stage |  | Tex
18 | 695571_1_En | Kalmani, Vijay | S200 | 2026-09-30 | 28 | 15 | [5 empty] | 48 | 550 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 13 Chapters; Comp : 35 Chapters; Online Delivery : 00 Chapters | Login reinstated, workflow issue solved |  |  | Tex+word
19 | 706742_1_En | Sahraoui, Zakaria-8770559 | S200 | 2026-09-30 | 28 | 16 | [5 empty] | 40 | 450 | S200 - Login : 01 Chapters; PE : 21 Chapters; CE : 18 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | Query chap 28. figs missing was reced. |  | Word
20 | 704411_1_En | Karakoc-AEF-8770589 | S200 | 2026-10-12 | 16 | [6 empty] | 31 | 350 | S200 - Login : 00 Chapters; PE : 30 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | Login moved on 29-Oct | New manuscript recd again and chap-31 added. On 12-Oct26. Preface & TOC(FM components missing), Index tagging for 2 chaps. missing reced on 28-oct | FM & TOC will be recd in S200 stage | Word
21 | 710147_1_En | Cheshmehzangi, Ali | S200 | 2026-10-12 | 16 | 9 | [5 empty] | 28 | 500 | S200 - Login : 00 Chapters; PE : 28 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Word
22 | 708159_1_En | Martín-Rojas, Rodrigo | S200 | 2026-10-07 | 21 | 9 | [5 empty] | 36 | 450 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 36 Chapters; Online Delivery : 00 Chapters
23 | 707038_1_En | Teba, Tarek | S200 | 2026-10-14 | 14 | 6 | [5 empty] | 42 | 500 | S200 - Login : 00 Chapters; PE : 42 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Word
24 | 708552_1_En | Gunka, Volodymyr | S200 | 2026-10-17 | 11 | 6 | [5 empty] | 23 | 350 | S200 - Login : 00 Chapters; PE : 23 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Word
25 | 700862_1_En | PERARNAU-DMD-Garcia-Sanchez | S200 Login | 2026-10-17 | 11 | [6 empty] | 56 | 300 | S200 - Login : 47 Chapters; PE : 09 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Tex
26 | 713085_1_En | Lo Presti, Davide | S200 Login | 2026-10-21 | 7 | [6 empty] | 109 | 350 |  |  |  |  | Word
27 | 710384_1_En | De Marchi, Luca | S200 Login | 2026-10-21 | 7 | 3 | [5 empty] | 69 | 400 | S200 - Login : 36 Chapters; PE : 33 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Tex
28 | 713564_1_En | AL-Emran-Ihalanayake Ranjith | S200 | 2026-10-17 | 11 | 6 | [5 empty] | 33 | 450 | S200 - Login : 00 Chapters; PE : 33 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  |  |  | Word
29 | 717901_1_En | Barla, Marco | S5 | 2026-10-21 | 7 | [6 empty] | 21 | 150 |  |  |  |  | Word
30 | 701850_1_En | Zi,-PIC Yunlong 8770448 | S5 | 2026-10-26 | 2 | [6 empty] | 12 | 150 |  |  |  |  | Word
31 | 704476_1_En | Zhan-Ventura, Michele Della-8770452 | S5 | 2026-10-27 | 1 | [6 empty] | 20 | 450 |  |  |  |  | Word
32 | 704485_1_En | González, Carina S. González | S50 | 2026-10-27 | 1 | [6 empty] | 16 | 200 |  |  |  |  | Word
33 | 707996_1_En | Ullah, Abrar | S5
34 | 697730_1_En | Hameed, Alaa Ali | S5 | [15 empty] | Rahul
Formulas:
Current TAT (S50 onward) = TODAY()-[Received Date (S50)]

## Delivered
S. no | Book ID | MPS ID | Stage | Received Date (S50) | Total Avg. Aging Days | Total Avg.Aging Days in S200 | S300A TAT | S300 TAT | S600 TAT | S650A TAT | S650 TAT | Total Chapters | MS Pages | TS Pages | Status - S200 | Status - 300 | Delivered Date | Remarks
1 | 704190_1_En | Mindeguia-SCFE-8770433 | S650 | 2026-06-29 | 63 | 32 | 11 | 3 | 6 | 6 | 5 | 6 | 184 | 385 | S200 - Delivered on 30th July Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: 00 Chapters | 2026-08-31
2 | 703415_1_En | Wen-NFE-8770557 | S650 | 2026-07-06 | 62 | 24 | 14 | 1 | 3 | 7 | 7 | 44 | 569 | 587 | S200 - Delivered on 01st Aug Login : 00 Chapters; PE : 00 Chapters; CE: 00 Chapters; Comp: 00 Chapters Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: | 2026-09-07
3 | 701319_1_En | Wang-AIS-Vol1-8770451 | S650 | 2026-06-22 | 83 | 33 | 13 | 5 | 13 | 10 | 8 | 66 | 717 | 719 | S200 - Delivered on 25th July Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Delivered on 12th Aug Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: 00 Chapters | 2026-09-12
4 | 701541_1_En | Wang-AIS-Vol2-8770450 | S650 | 2026-06-23 | 81 | 36 | 12 | 8 | 5 | 11 | 9 | 74 | 826 | 847 | S200 - Delivered on 30th July Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: 00 Chapters | 2026-09-13
5 | 701545_1_En | Wang-AIS-Vol3-8770449 | S650 | 2026-06-22 | 85 | 37 | 13 | 3 | 10 | 11 | 11 | 65 | 802 | 785 | S200 - Delivered on 29th July Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: 00 Chapters | 2026-09-15
6 | 659832_1_En | Iacomini-AIMN-8770513 | S650 | 2026-07-31 | 52 | 24 | 12 | 4 | 6 | 3 | 2 | 10 | 250 | 225 | S200 - Delivered on 24th Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 02 Chapters; Online Delivery : 00 Chapters Delivered: 08 Chapters | 2026-09-21
7 | 688480_1_En | Mukandavire, Zindoga | S650 | 2026-07-27 | 58 | 21 | 8 | 12 | 6 | 9 | 2 | 21 | 780 | 385 | S200 - Delivered on 17th Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : FM Delivered: 20 Chapters | 2026-09-23 | Moved to accessibility on 21st
8 | 710736_1_En | Iadanza, Ernesto-8770689 | S650 | 2026-08-10 | 47 | 19 | 14 | 1 | 6 | 1 | 6 | 64 | 700 | 719 | S200 - Delivered on 31st Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-09-26 | Fixed Pub Date - 25th Sep
9 | 710724_1_En | Iadanza, Ernesto-8770719 | S650 | 2026-08-12 | 44 | 15 | 15 | 2 | 6 | 1 | 2 | 55 | 700 | 889 | S200 - Delivered on 27th Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-09-25 | Fixed Pub Date - 25th Sep
10 | 710919_1_En | Iadanza, Ernesto-8770888 | S650 | 2026-08-24 | 37 | 16 | 5 | 1 | 7 | 0 | 7 | 60 | 500 | 819 | S200 - Delivered on 9th Sep Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-09-30 | Fixed Pub Date - 01st Oct- Jobsheet updation requitred, QIRA raised on 28th Sep
11 | 706767_1_En | Ivanov, Vitalii-V1 | S650 | 2026-08-18 | 46 | 27 | 4 | 4 | 4 | 3 | 2 | 25 | 500 | 465 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-10-03 | Fixed Pub Date - 24th Sep, S600 awaited (Job sheet issue)
12 | 706769_1_En | Ivanov, Vitalii-V2 | S650 | 2026-08-20 | 42 | 25 | 5 | 2 | 0 | 1 | 8 | 25 | 500 | 295 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-10-01 | Fixed Pub Date - 24th Sep
13 | 706770_1_En | Ivanov, Vitalii-V3 | S650 | 2026-08-25 | 37 | 19 | 5 | 0 | 4 | 2 | 5 | 35 | 500 | 343 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-10-01 | Fixed Pub Date - 24th Sep
14 | 634063_1_En | Tortorella-PGMP1-8770423 | S650 | 2026-07-01 | 97 | 33 | 24 | 7 | 7 | 18 | 7 | 2 | 317 | 299 | S200 - Delivered on 03rd Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 00 Chapters Delivered: 00 Chapters | 2026-10-06
15 | 702137_1_En | Tortorella-PGMP2-8770424 | S650 | 2026-07-01 | 103 | 35 | 23 | 10 | 4 | 18 | 5 | 6 | 302 | 333 | S200 - Delivered on 05th Aug Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters | S300 - Comp : 00 Chapters; Online Delivery : 01 Chapters Delivered: 05 Chapters | 2026-10-12
16 | 703192_1_En | Bhat, Vijay Kumar | S650 | 2026-08-31 | 44 | 31 | 6 | 2 | 3 | 3 | 4 | 25 | 500 | 385 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-10-14
17 | 691371_1_En | Zawawi, Iskandar Shah Mohd | S650 | 2026-09-04 | 52 | 22 | 15 | 4 | 7 | 3 | 1 | 14 | 189 | 201 | S200 - Login : 00 Chapters; PE : 00 Chapters; CE : 00 Chapters; Comp : 00 Chapters; Online Delivery : 00 Chapters |  | 2026-10-26

## Summary
DESCriptions | Column1 | Overall Avg. Aging days
SUMMARY |  | Overall Avg. Aging days
Total No of Titles in WIP | 34 | 24.4688
Total Titles Delivered | 17 | 61.3125
Month/No Of Titles | S200 | S300A | S300 | S600 | S650A | S650 | Total Monthly Avg. Aging days
Aug, 1 Book | 32 | 11 | 3 | 6 | 6 | 5 | 63
Sep, 9 Books | 25 | 11.7778 | 4.1111 | 6.8889 | 5.8889 | 6 | 61
Oct 7 Books | 27.4286 | 11.7143 | 4.1429 | 4.1429 | 6.8571 | 4.5714 | 60
Average Aging Days for past months | 28.1429 | 11.4974 | 3.7513 | 5.6772 | 6.2487 | 5.1905
Shortest TAT | 37
Longest TAT | 103
S200 | 13 Books
S300A | 3 Books
S300 | 7 Books
S600 | 2
S650 A | 2
S650 | 1

## Month Wise Delivery Status
Month Wise Delivery Status
Total No.of Titles | 15
Month | No of titles delivered
2026-08-01 | 1
2026-09-01 | 9
2026-10-01 | 7
2026-11-01 | 0
2026-12-01 | 0

## MISC
S. no | Book ID | S300A TAT(Target:10) | S300 TAT(Target:7) | S600 TAT(Target:7) | S650 TAT(Target:7) | Total TAT | Action Required | Remarks
1 | 634063_1_En | 24 | 7 | 7 |  | #REF! | On Track. 37 days buffer
2 | 702137_1_En | 23 | 10 | 4 |  | #REF! | On Track. 38 days buffer
3 | 688480_1_En | 8 | 12 | 6 | 2 | 58 | On Track. 47 days buffer | Released on 22-Sep
4 | 659832_1_En | 12 | 4 | 6 | 3 | 52 | On Track. 50 days buffer | Released on 21-Sep
5 | 710724_1_En | 15 | 1 | 6 | 4 | 44 | On Track. 49 days buffer | Released on 25-Sep
6 | 710736_1_En | 14 | 1 | 6 | 6 | 47 | On Track. 48 days buffer | Released on 26-Sep
7 | 706770_1_En | 5 | 0 | 4 | 33 | #REF! | On Track. 33 days buffer
8 | 706769_1_En | 5 | 41 |  |  | #REF! | On Track. 34 days buffer
9 | 706767_1_En | 5 | 41 |  |  | #REF! | On Track. 34 days buffer
10 | 710919_1_En | 5 | 1 | 42 |  | #REF! | On Track. 32 days buffer
11 | 705744_1_En |  |  |  |  | #REF! | Not Started
12 | 703192_1_En |  |  |  |  | #REF! | Not Started
13 | 691371_1_En |  |  |  |  | #REF! | Not Started
14 | 695893_1_En |  |  |  |  | #REF! | Not Started
15 | 695444_1_En |  |  |  |  | #REF! | Not Started
16 | 695897_1_En |  |  |  |  | #REF! | Not Started
17 | 696264_1_En |  |  |  |  | #REF! | Not Started
18 | 696262_1_En |  |  |  |  | #REF! | Not Started
19 | 696258_1_En |  |  |  |  | #REF! | Not Started
20 | 696260_1_En |  |  |  |  | #REF! | Not Started
21 | 696253_1_En |  |  |  |  | #REF!
22 | 708036_1_En |  |  |  |  | #REF!
23 | 702839_1_En |  |  |  |  | #REF!
24 | 704353_1_En |  |  |  |  | #REF!
25 | 708652_1_En
26 | 709492_1_En
27 | 702446_1_En
|  | WIP | 33
|  | Delivered | 17 | Overall Avg. Aging 61 days
| SL. No | MPS ID | Stage | Current TAT (S50 onward) | Remarks
| 1 | Sánchez, Angeles | S600 | 64
| 2 | Giordano, Andrea | S650A | 40
| 3 | Metsoc Vol-V-8771050 | S300 | 39
| 4 | Metsoc Vol-VI-8771051 | S600 | 39
| 5 | Metsoc Vol-VII-8771052 | S300 | 39
| 6 | Abarzhi, Snezhana I. | S650A | 36 |  | 696263_1_En | MetSoc-Vol9-8771159 | 30 | PageProof-S200 | PMApproval
| 7 | Metsoc Vol-III-8771048 | S300 | 34 |  | 696263_1_En | MetSoc-Vol9-8771159 | 46 | PageProof-S200 | PMApproval
| 8 | Metsoc Vol-IV-8771049 | S300A | 34 |  | 696263_1_En | etSoc-Vol9-8771159 | 58 | PageProof-S200 | PMApproval
| 9 | Metsoc Vol-VIII-8771060 | S300 | 33
| 10 | Metsoc Vol-I-8771046 | S300 | 31
| 11 | Metsoc Vol-II-8771047 | S300A | 31
| 12 | Bibri, Simon Elias | S300A | 31
| 13 | Trapani, Ferdinando | S300A | 30
| 14 | Zhou, Kun-8770838 | S300A | 29
| 15 | García-Holgado, Alicia-8771063 | S200 | 28
| 16 | Metsoc-Vol-IX-8771159 | S200 | 27
| 17 | Kalmani, Vijay | S200 | 27
| 18 | Sahraoui, Zakaria-8770559 | S200 | 27
| 19 | Xu-MSEM-8771092-Tex | S200 | 20
| 20 | Martín-Rojas, Rodrigo | S200 | 20
| 21 | Karakoc-AEF-8770589 | S200Login | 15
| 22 | Cheshmehzangi, Ali | S200 | 15 | Hold for Manuscript
| 23 | Teba, Tarek | S200 | 13
| 24 | Gunka, Volodymyr | S200 | 10
| 25 | PERARNAU-DMD-Garcia-Sanchez | S200 Login | 10
| 26 | AL-Emran-Ihalanayake Ranjith | S200 | 10
| 27 | Lo Presti, Davide | S200 Login | 6
| 28 | De Marchi, Luca | S200 | 6
| 29 | Barla, Marco | S5 | 6
| 30 | Zi,-PIC Yunlong 8770448 | S5 | 1
| 31 | Zhan-Ventura, Michele Della-8770452 | S5 | 0
| 32 | González, Carina S. González | S5 | 0
| 33 | Ullah, Abrar | S5 | 0